## Sheet1
Feedback of UAT performed on 12th & 13th January, 2017
Sr. No. | Observations | TAB/Page
1 | Category Name search if vendor is searching in wrong category - help is to be given. Smart search is needed for finding the Key word search. | Category Details
2 | Reverse linking for category and Discipline is required (Linking from Category to Discipline is to be done) | Category Details
3 | Category Name search % -Vendor should be able to search without prefixing/suffixing % sign | Category Details
4 | Discipline wise Category details to be shown as pdf report as a help (Evosys will generate pdf report which would be fetched dynamically from the view provided by IFFCO) | Category Details
5 | Dynamic label change in Currency and Turnover in Crore, Currency Column to be removed | Finance Details
6 | Label Change for "Registered Since" to "Currently Registered Since", Change LOV To Text Box, Input format will be YYYY only numeric(year) | REG with other companies
7 | Add a note for vendor to enter only current registrations with companies, IFFCO to provide exact Note | REG with other companies
8 | Provision of Last Five Years for Financial Details LOV | Finance Details
9 | Add OTHERS in Discipline LOV, Add Other Caetgory option should be available only when Discipline selected is Others | REG with other companies
10 | Change lable from IS and BIS to IS/BIS | Certification details
11 | Add Vendor Type as column identifying on enclosure page | Enclosure
12 | Delete option should be hidden except for additional Document Details | Enclosure
13 | Change label "Company" & "Vendor" word with "Supplier" | Through out application+Report
14 | Change Label of Button to (Validate and Print) instead of (Print and Validate) | Final Submission
15 | Give Acknowledment/Confirmation Message before final submission | Final Submission
16 | Help icon inside Instructions, as a link for Help | Instructions
17 | Please update Golden Jublee Logo, Dynamic Updation For Logo, for all screens and report | Through out both applications
18 | In Tax Detail Validation should get fired on Tab Out / on navigation to other column | Tax Details
19 | In Sign Up Page, Validations should get fired on tab out / on navigation to other column | Sign Up Page
20 | Cancelled Cheque should be mandatory, as Bank Details are mandatory | Bank Details
21 | Category Description should be visible once selected or give the pre selected values. | Category Details
22 | Data should be saved as draft, once Ok Button is Clicked in Category Pop Up | Tax Details
23 | IFFCO has provided validation of tax details. It has to be incorporated. | Tax Details
24 | Report change for Contact Details, only those details should be visible which have been submitted. | Report
25 | All the categories are getting displayed in report, instead of selected category. Which is to be corrected. | Report
26 | When the text is in Readonly mode and it is not getting displayed completely due to size limitation, A Popup should display with complete details, on mouse hover/mouse click. | Through out application
27 | PO Name to be renamed to Post Office Name | Through out both applications
28 | All the Tax Details related to GST is not appearing in report. | Report
29 | Category Details- For Each discipline separate block should be displayed , with Category Description and other fields should be available in Report | Report
30 | In Reports Finance Details section Turnover is coming in Millions which is to be corrected. | Report
31 | Place Application Id in the Reports First Block | Report
32 | In Header of each page, there should be Supplier Name, Application Id, PAN should be displayed; New Vendor Registration label should be removed | Report
33 | View Units In Forward Page to be displayed | Forward Page
34 | There is some issue while Forwarding To Second Time for Same Coordinator. | Forward Page
35 | Place Creation Time Stamp and Notification ID for each lowest level users request View Status Page | View Status
36 | Pending Count is not getting Refreshed when forwarded Second Time. | View Status
37 | Action Date in Lowest Level Users should hide when Notification is still in Pending Stage | View Status
38 | Radio Button should not be given, directly IFFCO User LOV should open for Users except Coordinator | Clarification For Application
39 | "To Member" to be changed from "IFFCO User Label" | Clarification For Application
40 | IFFCO User LOV in clarification list to be bifurcated in Clarification with Unit Name | Clarification For Application
41 | Personal No - User Name in IFFCO User LOV to be shown | Clarification For Application
42 | Text search in LOV should be enabled with "starts with the text entered" for each LOV, throughout both applications | Clarification For Application
43 | Add attachment under Add Clarification in application Specific Clarification | Clarification For Application
44 | Recepient: Personal No-To User Name Instead of List Of Recepeints | Clarification For Application
45 | Notification Date to be replaced with Action Date, in Search Region Label | Notification Region
46 | Uniform date format dd-MM-yyyy in Notification Search Region and throughout Application to be given | Notification Region
47 | Notification Table to be Given Instead of Notification List View, with Sort Option And Filter Option On Top | Notification Region
48 | In Attachments Section, before uploading files Put a Validation on file size and file types as mentioned below- Total File Size for single application should not be greater than 15MB (Each File not more than 3 MB), File Types Allowed: JPEG,PNG,DOCx, PDF,XLSX,Txt | Enclosures
49 | Department Name & Section of HRMS Sytem in Master Setup For Wrokflow to be given | Master
50 | Indenter may have many types, role should be disaplyed inside foraward page | Forward Page
51 | SYS Admin role should be available which may be given to Unit IT Heads (Unit IT Head may be given a role which is required for any changes required in master module, it is assumed that Unit IT Head would make some changes only upon specific request received by him)
52 | If the user is already logged In from one system, he should Only be allowed to login when earlier session is forced log Out. | Login
53 | Recommendation- Two Radio Button to be given - Recommend Yes/No, Remarks to be made mandatory in case of " Not Recommended" | Through out applicaion
54 | Rejected Count, Approved Count, Pending Count to be removed in View Status | View Status
55 | a) Recommended and Not Recommended button for all peoples in the Workflow except O2. b) For O2, Approve Reject c) remove cancel Button in O3, only one button Push To EBS. | Through out applicaion
56 | "Supplier Approved Selection" instead of "VR Selection", Label to be changed | View Status
57 | The alignment of the text to be made justified throughout the application in display (especially in Remarks Column) | Through out applicaion
58 | O1 Selection and Supplier Selction (Union) should be copied to O2 in Unit Selecion | Unit Selection
59 | Unit Head Recommendation to be displayed in Unit Selection Popup | Unit Selection
60 | Application Approved Succssfully popup to be given for O2 | Approval
61 | URL Password Label to be changed | Email
62 | Unit Details and Category Selection to be given inl Email notifications given to the Supplier with CC to IFFCO committees | Email
63 | Digital Key "Yes"/"No" to be taken to EBS through interface | EBS Integration
64 | HRMS Password should be used as it is in Application for IFFCO User | Login
65 | For Foregin Supplier, Banking Details and Tax Details should be made invisible and validations should not fire for the same and accordingly Integration API should be updated | Bank Details, Tax Details
66 | Provision of Central Unit to be given alongwith Head Office Unit | Master
67 | Users List form HRMS User, in Employee Details Page, Evosys yet to confirm why they developed Employee Master Page | Master
68 | Values in LOV to be given : Commercial/Purchase, Finance, Indentor, Technical and Chairman (the values for Department Type in Committee Setup Page for which provision to be made) | Master
69 | Second Apoprover Label to be changed to Approver, third approver label change to SYSADMIN | Master
70 | Proprietary category of GSL not to be shown on Supplier Registration system, view needs to be changed by IFFCO

## Sheet2
Add OTHERS in Discipline LOV, Add Other Caetgory option should be available only when Discipline selected is Others